## Sheet1
# | Risk Item | Risk Resolution Measures | Justification
1 | Personnel shortfalls | Qualiuty Staffing, team building, employee wellfare. | The size of the team matters and having each member present and giving their full attention to the project is extremely important.
2 | Developing a wrong piece | Cover the clients wants during briefings, have prototypes with end user feedback to prevent further development if incorrect. | Creating early and functional inferfaces for end users to test to make sure the intended product is on track can prevent re devlopment futher down the cycle
3 | Frequent changes to product | If frequent changes are forcing development to miss deadlines, defer to future updates/builds. | if interfaces are continually asked to be changed they can cause development to miss deadlines leading to fees.
4 | External product sources | Communicate to the outside source to ensure the database is efficient and the program will work with the data. | If issues arise with the database this would slow down the development because several parts rely on the database to function.
5 | High product requirments | Several builds and prototypes to ensure product is not above the required hardware specifications. | if the program require more resources than orginally planned for, fees/deadlines and re development could occur costing money.